## Gantt Data
Task | Start Week | Duration (Weeks) | Milestone
Planning & Documentation | 1 | 2
Requirements Analysis | 3 | 2
Requirements Approved | 5 |  | 0.1
System Design | 5 | 2
Design Complete | 7 |  | 0.1
Authentication Module | 7 | 1
User Profile & Address Module | 7 | 1
Pickup Request System | 8 | 1
Scheduling System | 8 | 1
AI Features Development | 9 | 1
Collector Dashboard | 9 | 1
Integration & API Connection | 9 | 1
Admin Dashboard | 10 | 1
Notification System | 10 | 0.5
Audit & Reporting | 10 | 0.5
System Ready | 11 |  | 0.1
Testing & QA | 11 | 2
Deployment Preparation | 11 | 0.5
Bug Fixing | 12 | 1
Deployment | 12 | 0.5
Final Submission | 13 |  | 0.1